Vanuatu Data Science Driving Innovation in Climate Change & Natural Disasters – Phase II

Concept Note

1. Overview

The Vanuatu Data Science Driving Innovation in Climate Change & Natural Disasters project, led by the Vanuatu Bureau of Statistics (VBoS) in partnership with the Ministry of Climate Change and Adaptation (MoCCA), Pacific Community (SPC), and a broad network of stakeholders, has created a strong foundation for data-driven climate change and disaster governance. In Phase I (2024–2025), the project established governance structures, conducted nationwide needs assessments, developed Reproducible Analytical Pipelines (RAPs) to automate cyclone damage and recovery cost estimation, initiated advanced machine learning (ML) training to monitor climate change indicators using satellite imagery, and commissioned the development of a Management Information System (MIS) to integrate these outputs into an operational decision-support platform.

2. Problem Statement

While Phase I delivered significant progress, important challenges remain. Many provincial stakeholders have yet to be trained to fully utilise the MIS and RAP for disaster preparedness, response, and recovery. The tools have not been stress-tested in operational conditions, limiting confidence in their real-time application. The RAP methodology currently focuses only on cyclones and has not been developed for other high-risk hazards such as earthquakes, volcanic eruptions, and tsunamis. Satellite-derived climate change indicators still require ground-truth validation to ensure accuracy. In addition, there is no formal mechanism for capturing end-user feedback and integrating it into regular updates for both the MIS and analytical methodologies.

3. Proposed Solution

Phase II will address these gaps through six interconnected components. First, Provincial MIS Training & Rollout will be implemented in all six provinces, providing hands-on training for government officials, community disaster committees, and civil society partners on data access, interpretation, use of predictive models, and integration into operational plans. Second, Annual Provincial Disaster Simulation Exercises will be conducted to simulate high-impact events, such as Category 4–5 cyclones, using MIS and RAP outputs to inform response and resource allocation. These drills will be evaluated to identify improvements in readiness and coordination.

Third, RAP Testing, Improvement & Expansion will be carried out to validate and refine cyclone damage and recovery estimation methodologies through field-testing during simulation exercises, and to expand the RAP to cover other hazards, including earthquakes, to enable multi-risk analytical capability. Fourth, Machine Learning Enhancement & Ground Verification will focus on improving the accuracy of climate change indicators, such as shoreline change, vegetation cover, and agricultural productivity, through refined machine learning models and field data collection to validate satellite-derived results.

Fifth, Improvements to MIS will ensure the platform continues to evolve as the central hub for climate and disaster data. Activities will include software development for new features and integrations, enhanced dashboard design and visualisation tools, security and data backup upgrades, and user acceptance testing based on feedback. A specialist consultant will also be engaged to design and implement automated data linkages with the MIS of other departments through secure API and SQL connections to government servers, reducing manual reporting burdens and ensuring real-time data flows across government systems.

Finally, a Continuous Improvement Cycle will be embedded through an annual MIS, ML, and RAP Review Workshop, ensuring that performance results, user feedback, and evolving hazard profiles are systematically used to guide system and methodological upgrades. This will include a dedicated week-long workshop each year to update and validate indicators inside the MIS, ensuring their ongoing policy relevance and alignment with evolving national priorities.

4. Expected Impact

The short-term impact of Phase II will include provincial stakeholders being fully trained and confident in using MIS, ML and RAP tools for decision-making, more accurate and hazard-inclusive damage estimates, and stronger inter-agency coordination through annual drills. In the long term, Vanuatu will have a multi-hazard, evidence-based decision-support system embedded in both national and provincial disaster management and climate adaptation processes. This will lead to faster, more efficient disaster responses that save lives, protect livelihoods, and minimise economic losses, while fostering a culture of continuous improvement in climate and disaster governance.

5. Estimated Budget (USD)

The total estimated cost for Phase II is USD 440,000 over a two-year programme. This includes USD 50,000 for provincial MIS, ML and RAP use training; USD 60,000 for annual disaster simulation exercises; USD 55,000 for expanding the RAP to cover additional hazards; USD 80,000 for ML enhancement and ground-truthing activities, USD 100,000 for improvements to the MIS; USD 40,000 for API/SQL integration; USD 30,000 for indicator update workshops; and USD 25,000 for continuation of the governance structure.

| Component | Activities | Budget |
| --- | --- | --- |
| Provincial MIS and RAP Use Training | - Airfares and transport - Venue hires and workshop catering - Printing of materials - Per diems - ICT equipment hire | 50,000 |
| Annual Disaster Simulation Exercises | - Airfares and transport - Venue hires and workshop catering - Logistics for scenario setup - Coordination meetings - Per diems - ICT equipment hire - Communication materials | 60,000 |
| Expansion of RAP for Other Hazards | - Technical consultancy to adapt RAP methodology for earthquakes, tsunamis, and volcanic eruptions - Stakeholder validation workshops - Training sessions for staff | 55,000 |
| Machine Learning Enhancement | - Specialist consultancy for refining algorithms and indicator accuracy - Field missions for ground-truthing data - Training sessions for staff in updated ML methods | 80,000 |
| Improvements to MIS | - Software development for new features and integrations - Enhanced dashboard design and visualisation tools - Security and data backup upgrades - User acceptance testing and refinement based on feedback | 100,000 |
| Specialist MIS Integration Consultancy | - Design and implement API/SQL integration with departmental MIS - Ensure secure server-to-server connections. - Reduce manual reporting burdens and enable real-time data flows | 40,000 |
| Annual Indicator Update Workshop | - Week-long national workshop - Update and validate MIS indicators - Ensure alignment with evolving national priorities and end-user needs | 30,000 |
| Continuation of Governance Structure | - Quarterly Steering Committee and Technical Committee meetings - Meeting venue hire and catering | 25,000 |
| Total |  | 440,000 |

6. Phase I Achievements to Phase II Priorities Mapping

| Phase I Achievements | Phase II Priorities |
| --- | --- |
| Governance structure established (Steering & Technical Committees) | Continue multi-stakeholder governance and embed feedback into MIS & RAP upgrades |
| Nationwide needs assessments conducted in all provinces | Deliver provincial-level MIS & RAP training based on identified needs |
| Development of RAP for cyclone damage and recovery estimation | Field-test RAP, refine methodology, and expand to earthquakes and other hazards |
| Launch of machine learning training for climate change monitoring | Enhance ML models and verify outputs through ground-truthing missions |
| Commissioning of MIS development to integrate RAP and ML outputs | Operationalise MIS in provinces and stress-test during annual disaster simulations |
| No systematic mechanism for cross-government data sharing in Phase I | Engage specialist consultancy to establish API/SQL integration with departmental MIS for real-time data flows |
| No structured process for annual MIS indicator validation in Phase I | Institutionalise annual week-long workshop to update and validate MIS indicators |